## Sheet1
LMS Workgroup January 2016 Meeting
Options and Timing for Canvas/OEI Decision & Course Migration
Cohort 3 Schedule/Timing
| - Sandbox testing | - LMS Workgroup evaluation | - Gather Faculty feedback |  | - LMS Workgroup Decision (May 2016) | - Begin IT Preparation (Integration with PeopleSoft, publishers, Authentication with LRCCD W-IDs, etc.) |  | - Primary migration (faculty choice) - Select Faculty Training |  | - Begin full Faculty training |  |  | - Early adopter courses live on Canvas or one initial course for faculty |  |  |  |  | - Additional courses live on Canvas |  | - Most courses live on Canvas |  |  |  | - Final D2L usage for live courses | - Discontinue D2L Contract
One-year Parallel Canvas/D2L Usage Period (faculty choice of migration timeline)
| Spring 2016 |  |  |  |  | Summer 2016 |  | Fall 2016 |  |  |  |  | Spring 2017 |  |  |  |  | Summer 2017 |  | Fall 2017 |  |  |  |  | Spring 2018
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN
Cohort 4 Schedule/Timing
| - Sandbox testing | - LMS Workgroup evaluation | - Gather Faculty feedback | [6 empty] | - LMS Workgroup Decision (Oct 2016) | - Begin IT Preparation (Integration with PeopleSoft, publishers, Authentication with LRCCD W-IDs, etc.) |  |  |  | - Primary migration (faculty choice) - Select Faculty Training |  | - Begin full Faculty training | - Early adopter courses live on Canvas or one initial course for faculty |  | - Additional courses live on Canvas |  |  |  |  | - Most courses live on Canvas |  |  |  | - Final D2L usage for live courses | - Discontinue D2L Contract
One-year Parallel Canvas/D2L Usage Period (faculty choice of migration timeline)
| Spring 2016 |  |  |  |  | Summer 2016 |  | Fall 2016 |  |  |  |  | Spring 2017 |  |  |  |  | Summer 2017 |  | Fall 2017 |  |  |  |  | Spring 2018
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN
Flexibility
ð | Spring 2016 JAN: "Cohorts model is only a suggestion for the purposes of planning"
ð | Spring 2016 JAN: "A college/district can choose whatever adoption model they prefer to fit their timelines, existing LMS contract, faculty/student needs, etc."
Requirements
ð | Spring 2016 JAN: "The timeline between the start of the implementation and when the first students begin using Canvas can be no more than 9 months"
ð | Spring 2016 JAN: "The college has to turn off their legacy systems within 18 months of their students first using Canvas"